## Detail1
Details for Count of TASK ID - STATUS: Done
TASK ID | TASK NAME | DESCRIPTION | PRIORITY | STATUS | START DATE | DUE DATE | COMPLETION% | REMARKS
8 | Backup Flight Logs | Save flight recorder data to secure storage | Medium | Done | 2025-06-07 | 2025-07-07 | 1 | Archived successfully
3 | Test VHF Comm Radio | Perform operational checks on VHF #2 | High | Done | 2025-07-07 | 2025-08-07 | 1 | Passed all checks

## Sheet1
AVIONICS PERSONAL TRACKER
TASK ID | TASK NAME | DESCRIPTION | PRIORITY | STATUS | START DATE | DUE DATE | COMPLETION% | REMARKS | Completion Month
1 | Inspect pilot tubes | Check for blockages or leaks on aircraft #Q400-12 | High | In Progress | 2025-07-07 | 2025-09-07 | 50% | Waiting for test flight | Sep-2025
2 | Update NAV Database | Upload latest nav data to FMS for fleet aircraft | Medium | To do | 2025-07-07 | 2025-10-07 | 0% | Waiting for approval | Oct-2025
3 | Test VHF Comm Radio | Perform operational checks on VHF #2 | High | Done | 2025-07-07 | 2025-08-07 | 100% | Passed all checks | Aug-2025
4 | Verify ELT Battery | Confirm ELT battery expiry date and replace if needed | Low | To do | 2025-08-07 | 2025-11-07 | 0% | Waiting for parts | Nov-2025
5 | Prepare Maintenance Log | Compile all inspection records for supervisor signoff | Medium | In Progress | 2025-07-07 | 2025-09-07 | 70% | Need final approval | Sep-2025
6 | Calibrate Radio Altimeter | Perform calibration test on RA system | High | To do | 2025-09-07 | 2025-09-07 | 0% | Waiting for paper work | Sep-2025
7 | Troubleshoot HF Antenna | Diagnose Intermittent signal on HF radio | High | In Progress | 2025-07-07 | 2025-07-07 | 40% | Parts ordered | Jul-2025
8 | Backup Flight Logs | Save flight recorder data to secure storage | Medium | Done | 2025-06-07 | 2025-07-07 | 100% | Archived successfully | Jul-2025
9 | Inpect Wiring Connections | Visual check and continuity test of cockpit wiring harness | High | To do | 2025-08-07 | 2025-10-07 | 0% | Waiting for approval | Oct-2025
10 | Update Tech Library | Add new OEM manuals and bulletin to database | Low | In Progress | 2025-07-07 | 2025-12-07 | 20% | Need final files from supplier | Dec-2025
11 | Install FMS System | Installation of the FMS System on the aircraft | Medium | In Progress | 2025-08-07 | 2025-09-07 | 45% | Waiting for paper work | Sep-2025
[7 empty] | Average Progress |  | Total Task
| Row Labels | Count of TASK ID |  |  |  |  | 38.64% |  | 11
| Done | 2 | 2
| In Progress | 5 | 5
| To do | 4 | 4 | [5 empty] | Last Updated: 13-Jul-2025
| Grand Total | 11 | Done: 2 In Progress: 5 To Do: 4

## pivots
Product of Average Progress |  |  | Count of TASK ID | Column Labels
38.64% | 38.64% |  | Row Labels | Done | In Progress | To do | Grand Total
|  |  | High | 1 | 2 | 2 | 5
|  |  | Low |  | 1 | 1 | 2
Sum of Total Task |  |  | Medium | 1 | 2 | 1 | 4
11 | 11 |  | Grand Total | 2 | 5 | 4 | 11
Row Labels | Count of TASK ID |  |  | Row Labels | Count of TASK ID
Done | 2 | 0 |  | Aug-2025 | 1
In Progress | 5 |  |  | Dec-2025 | 1
To do | 4 |  |  | Jul-2025 | 2
Grand Total | 11 |  |  | Nov-2025 | 1
|  |  |  | Oct-2025 | 2
Overdue Tasks: 0 |  |  |  | Sep-2025 | 4
|  |  |  | Grand Total | 11
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard
AVIONICS TASK TRACKER DASHBOARD
11
39%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Done: 2 In Progress: 5 To Do: 4
TASK OVERVIEW
Average Progress
TOTAL TASK
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Last Updated: 13-Jul-2025
Update Task Status Daily
Prepared by: Alabi Timilehin
Role: Avionics Engineer
Overdue Tasks: 0